## Sheet1
Performance Objective #2 |  |  |  |  | Project Management
2.1a Construction Project Performance for Projects Greater than $500k
Project Name |  |  |  | TEC ($K)
Replace Linac (VVS) (2GPP & 14 SLI) |  |  |  | 1090 | 239 FY04 | Cost ($K) |  |  | Completion Schedule
(15 total @ $545K/ea) | [5 empty] | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [8 empty] | 2004-05-01
Engineering | [5 empty] | 20 |  |  | 2005-12-05
Procurement | [5 empty] | 172 |  |  | 2005-07-01
Light Assembly Bldg (033) Substation |  |  |  | 740 | 556 FY04 | Cost ($K) |  |  | Completion Schedule
[6 empty] | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [8 empty] | 2003-12-01 | 2004-01-01
ED&I/Project Management | [5 empty] | 54 |  |  | 2004-10-01
Procurement | [5 empty] | 219 |  |  | 2004-06-01
Construction | [5 empty] | 128 |  |  | 2004-08-01
Testing | [8 empty] | 2004-09-01
Beneficial Use | [8 empty] | 2004-09-01
Project Completion | [8 empty] | 2004-10-01
Upgrade Substation 7 |  |  |  | 930 | 435 FY04 | Cost ($K) |  |  | Completion Schedule
[6 empty] | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [8 empty] | 2002-02-01 | 2002-02-01
ED&I/Project Management | [5 empty] | 21 |  |  | 2004-12-01
Procurement | [5 empty] | 80 | 80 |  | 2003-12-01 | 2003-12-01
Construction | [5 empty] | 180 |  |  | 2004-05-01
Installation | [5 empty] | 70 |  |  | 2004-11-01
Testing | [8 empty] | 2004-12-01
Beneficial Use | [8 empty] | 2004-12-01
Project Completion | [8 empty] | 2004-12-01
S&ORI Project (FY04 Line Item) |  |  |  | 15600 | 1988 FY04 | Cost ($K) |  |  | Completion Schedule
[6 empty] | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [8 empty] | 2003-10-01 | 2004-01-01
Title I Design | [5 empty] | 550 |  |  | 2004-07-01
EIR | [8 empty] | 2004-10-01
Title II Design | [5 empty] | 750 |  |  | 2004-11-01
[8 empty] | TOTAL: |  |  | 0
Month |  | Excellent | Satisfied | Ok
| Percentage Satisfied |  |  |  | Not Satisfied | Please Call Me | Percentage Of Customers Responding
2003-09-01 | 97% | 62 | 11 | 1 | 1 | 1 | 5.933%
2003-10-01 | 92% | 69 | 8 | 1 | 2 | 5 | 5.52%
2003-11-01 | 99% | 61 | 13 | 1 | 1 | 0 | 6.623%
2003-12-01 | 95% | 33 | 8 | 0 | 0 | 2 | 4.571%
2004-01-01 | 93% | 65 | 8 | 4 | 2 | 4 | 5.985%
2004-02-01 | 98% | 69 | 7 | 4 | 1 | 1 | 6.845%
2004-03-01 | 97% | 69 | 17 | 3 | 3 | 0 | 5.569%
2004-04-01 | 99% | 46 | 21 | 0 | 1 | 0 | 4.797%
2004-05-01 | 97% | 54 | 11 | 3 | 0 | 2 | 5.825%
2004-06-01 | 98% | 77 | 5 | 1 | 1 | 1 | 7.527%
2004-07-01 | 94% | 42 | 6 | 1 | 0 | 3 | 4.709%
2004-08-01 | 97% | 47 | 19 | 1 | 0 | 2 | 4.43%
2004-09-01 | 91% | 12 | 8 | 0 | 2 | 0 | 2.632%
Satisfaction Level | 95.92%
Month | Service Calls Per Month
2004-09-03 | 1045
2003-10-01 | 1250
2003-11-01 | 921
2003-12-01 | 722
2004-01-01 | 1086
2004-02-01 | 1008
2004-03-01 | 1239
2004-04-01 | 959
2004-05-01 | 927
2004-06-01 | 1023
2004-07-01 | 892
2004-08-01 | 1061
2004-09-01 | 456
Average Volume | 968.3846