## Slide 1: HGVPU Preparations
Zack Wolf
4/1/16

## Slide 2: Undulator Placement
Stand removed
MMF orientation same as tunnel orientation.
Steve Score
Yurii Levashov

## Slide 3: Undulator Placement
Undulator 12 inches from granite.
We can make adjustments on back of undulator.
Tuning done from front.

## Slide 4: Undulator Placement
No interference with Kugler bench.

## Slide 5: Undulator Placement
Pedestal locations.

## Slide 6: Arm For Probes
Yurii Levashov
Scott Jansson

## Slide 7: Arm For Probes
Small goniometer
Small rotary stage
Ceramic

## Slide 8: Arm Vibration Within Tolerance
“If the arm is 0.5m long than the z location has an RMS of 1.2µm.” Georg
ΔB ~ ku B0 Δz ~ 3 Gauss
LCLS-TN-04-8 Require pitch and yaw < 4.2 μrad
High frequency.
Does not affect K.
Georg Gassner

## Slide 9: Rotate Equipment For Probes
Locate Hall Elements
Zero Gauss Chambers

## Slide 10: Approximate Short Term Timeline
Friday 4/1: review, get BIO approval for anchors, order any parts, mark floor for holes
Monday 4/4: drill holes for pedestals, undulator arrives
Tuesday 4/5: mount pedestals, align cam movers
Wednesday 4/6: mount undulator
Thursday 4/7: controls setup
Friday 4/8: controls setup
Mon-Fri 4/11-4/15: monitor shelf as gap changes
Mon- Fri 4/18-4/29: measure undulator, compare to ANL
~5/1: send undulator to LBNL

## Slide 11: Planned Production Workflow
SXU blue
HXU purple

## Slide 12: Reference Undulators
Have two fixed gap LCLS
undulators.
Will replace tapered shims with
flat shims.
Rotate HXU reference.

## Slide 13: HGVPU CMM Work
Finish the fiducialization
Measure the gap
Install / straighten the beam pipe
Install / align the interspace components

## Slide 14: Partial List Of Open Issues
Lock and tag during tuning.
Undulators must come fully protected. All parameters must be set. All limit switches must be set and tested. If we change an encoder offset, a switch must protect against a typing error.
We need controls at the benches, at the CMM, and at an undulator setup area. The controls will be used simultaneously so they cannot be moved.
Store HXU undulators on kinematic mounts.
HXU tuning ergonomics.

## Slide 15: End