## Start Oct 2und
Parameters
Start of upgrades | [10 empty] | Oct 8th 2024
PAMM frequency | [10 empty] | Every 4 weeks
Upgrade Spare Undulator early | [10 empty] | No
Remove 2 Undulator on first PAMM | [10 empty] | No
Minimum of Short length undulator equivalent | [10 empty] | 18
Upstream Cells ready for undulators | [10 empty] | April 2025
2 undulators gets removed from the UH on Sept 1st
Date | [35 empty] | #SX | #HE | # Short periode und before/after SXRSS
| Cell | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 |  |  | before | after | # Short periode und
2024-09-01 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | U | U | U | U | U |  |  |  | 21 | 2 | 10.3333 | 12 | 22.3333 |  | U | … | LCLSII SXR Undulator
2024-10-08 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | U | U | U | U | HE |  |  |  | 20 | 3 | 10.3333 | 11.6667 | 22 |  | HE | … | LCLSII-HE SXR Undulator
2024-12-03 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | U | U | U | HE | HE |  |  |  | 19 | 4 | 10.3333 | 11.3333 | 21.6667 |  | 7 | … | Not enough undulators before SXRSS
2024-01-04 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | U | U | HE | HE | HE |  |  |  | 18 | 5 | 10.3333 | 11 | 21.3333 |  | SS | … | SXRSS Girder
2025-02-25 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | U | HE | HE | HE | HE |  |  |  | 17 | 6 | 10.3333 | 10.6667 | 21 |  | Delta | … | Other
2025-03-25 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | HE | HE | HE | HE | HE |  |  |  | 16 | 7 | 10.3333 | 10.3333 | 20.6667
2025-04-22 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | HE | HE | HE | HE | HE | HE |  |  |  | 15 | 8 | 10.3333 | 10 | 20.3333
2025-05-20 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 14 | 9 | 10.3333 | 9.6667 | 20
2025-06-17 | [7 empty] | HE | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 14 | 10 | 11 | 9.6667 | 20.6667
2025-06-17 | [6 empty] | HE | HE | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 14 | 11 | 11.6667 | 9.6667 | 21.3333
2025-07-15 | [6 empty] | HE | HE | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 13 | 12 | 11.6667 | 9.3333 | 21
2025-08-12 | [6 empty] | HE | HE | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 12 | 13 | 11.6667 | 9 | 20.6667
2025-08-12 | [6 empty] | HE | HE | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 11 | 14 | 11.6667 | 8.6667 | 20.3333
2025-09-09 | [6 empty] | HE | HE | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 10 | 15 | 11.6667 | 8.3333 | 20
2025-10-07 | [6 empty] | HE | HE | HE | HE | U | U | U | U | SS | U | U | U | U | HE | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 9 | 16 | 10.6667 | 8.3333 | 19
2025-10-07 | [5 empty] | HE | HE | HE | HE | HE | U | U | U | U | SS | U | U | U | U | HE | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 9 | 17 | 11.3333 | 8.3333 | 19.6667
2025-11-04 | [5 empty] | HE | HE | HE | HE | HE | U | U | U | U | SS | U | U | U | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 8 | 18 | 11.3333 | 8 | 19.3333
2025-11-04 | [5 empty] | HE | HE | HE | HE | HE | U | U | U | U | SS | U | U | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 7 | 19 | 11 | 8 | 19
2025-12-02 |  |  |  |  | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | U | U | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 7 | 20 | 11.6667 | 8 | 19.6667
2025-12-30 |  |  |  |  | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | U | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 6 | 21 | 11.3333 | 8 | 19.3333
2026-01-27 |  |  |  |  | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 5 | 22 | 11 | 8 | 19
2026-02-24 |  |  |  | HE | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 5 | 23 | 11.6667 | 8 | 19.6667
2026-03-24 |  |  | HE | HE | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 5 | 24 | 12.3333 | 8 | 20.3333
2026-03-24 |  |  | HE | HE | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 4 | 25 | 12 | 8 | 20
2026-04-21 |  |  | HE | HE | HE | HE | HE | HE | HE | HE | U | U | U | HE | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 3 | 26 | 9 | 11.3333 | 20.3333
2026-04-21 |  | HE | HE | HE | HE | HE | HE | HE | HE | HE | U | U | U | HE | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 3 | 27 | 9.6667 | 11.3333 | 21
2026-05-19 |  | HE | HE | HE | HE | HE | HE | HE | HE | HE | U | U | HE | HE | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 2 | 28 | 9.3333 | 11.3333 | 20.6667
2026-06-16 |  | HE | HE | HE | HE | HE | HE | HE | HE | HE | U | HE | HE | HE | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 1 | 29 | 9 | 11.3333 | 20.3333
2026-07-14 |  | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 0 | 30 | 8.6667 | 11.3333 | 20
Consolidated Schedule
Date | [35 empty] | #SX | #HE | # Short periode und before/after SXRSS
| Cell | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 |  |  | before | after | # Short periode und | IN |  | Out |  | Und | Days
2024-09-01 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | U | U | U | U | U |  |  |  | 21 | 2 | 10.3333 | 12 | 22.3333 | 2 |  | 0 |  | 00+N |  | U | … | LCLSII SXR Undulator
2024-10-08 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | U | U | U | U | HE |  |  |  | 20 | 3 | 10.3333 | 11.6667 | 22 | 1 |  | 1 |  | N |  | HE | … | LCLSII-HE SXR Undulator
2024-12-03 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | U | U | U | HE | HE |  |  |  | 19 | 4 | 10.3333 | 11.3333 | 21.6667 | 1 |  | 1 |  | 47 |  | 7 | … | Not enough undulators before SXRSS
2024-01-04 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | U | U | HE | HE | HE |  |  |  | 18 | 5 | 10.3333 | 11 | 21.3333 | 1 |  | 1 |  | N | 13 | SS | … | SXRSS Girder
2025-02-25 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | U | HE | HE | HE | HE |  |  |  | 17 | 6 | 10.3333 | 10.6667 | 21 | 1 |  | 1 |  | 46 | 36 | Delta | … | Other
2025-03-25 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | U | HE | HE | HE | HE | HE |  |  |  | 16 | 7 | 10.3333 | 10.3333 | 20.6667 | 1 |  | 1 |  | 45 | 19
2025-04-22 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | U | HE | HE | HE | HE | HE | HE |  |  |  | 15 | 8 | 10.3333 | 10 | 20.3333 | 1 |  | 1 |  | 44 | 19
2025-05-20 | [8 empty] | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 14 | 9 | 10.3333 | 9.6667 | 20 | 1 |  | 1 |  | 43 | 19
2025-06-17 | [6 empty] | HE | HE | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | U | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 14 | 11 | 11.6667 | 9.6667 | 21.3333 | 2 |  | 0 |  | 41+42 | 18
2025-07-15 | [6 empty] | HE | HE | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | U | U | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 13 | 12 | 11.6667 | 9.3333 | 21 | 1 |  | 1 |  | N | 18
2025-08-12 | [6 empty] | HE | HE | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 11 | 14 | 11.6667 | 8.6667 | 20.3333 | 2 |  | 2 |  | 40+N | 19
2025-09-09 | [6 empty] | HE | HE | HE | HE | U | U | U | U | U | U | U | U | U | SS | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 10 | 15 | 11.6667 | 8.3333 | 20 | 1 |  | 1 |  | 39 | 18
2025-10-07 | [5 empty] | HE | HE | HE | HE | HE | U | U | U | U | SS | U | U | U | U | HE | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 9 | 17 | 11.3333 | 8.3333 | 19.6667 | 2 |  | 1 |  | 38+37 | 19
2025-11-04 | [5 empty] | HE | HE | HE | HE | HE | U | U | U | U | SS | U | U | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 7 | 19 | 11 | 8 | 19 | 2 |  | 2 |  | 35+N | 19
2025-12-02 |  |  |  |  | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | U | U | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 7 | 20 | 11.6667 | 8 | 19.6667 | 1 |  | 0 |  | 36 | 17
2025-12-30 |  |  |  |  | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | U | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 6 | 21 | 11.3333 | 8 | 19.3333 | 1 |  | 1 |  | 34 | 13
2026-01-27 |  |  |  |  | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 5 | 22 | 11 | 8 | 19 | 1 |  | 1 |  | 33 | 15
2026-02-24 |  |  |  | HE | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | U | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 5 | 23 | 11.6667 | 8 | 19.6667 | 1 |  | 0 |  | 32+N | 18
2026-03-24 |  |  | HE | HE | HE | HE | HE | HE | HE | HE | U | U | U | U | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 4 | 25 | 12 | 8 | 20 | 2 |  | 1 |  | 2N | 19
2026-04-21 |  | HE | HE | HE | HE | HE | HE | HE | HE | HE | U | U | U | HE | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 3 | 27 | 9.6667 | 11.3333 | 21 | 2 |  | 1 |  | 31+N | 19
2026-05-19 |  | HE | HE | HE | HE | HE | HE | HE | HE | HE | U | U | HE | HE | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 2 | 28 | 9.3333 | 11.3333 | 20.6667 | 1 |  | 1 |  | 29 | 19
2026-06-16 |  | HE | HE | HE | HE | HE | HE | HE | HE | HE | U | HE | HE | HE | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 1 | 29 | 9 | 11.3333 | 20.3333 | 1 |  | 1 |  | 28 | 19
2026-07-14 |  | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | SS | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | HE | Delta |  |  | 0 | 30 | 8.6667 | 11.3333 | 20 | 1 |  | 1 |  | 27 | 18
[41 empty] | 30 |  | 21
This year 4 new undulators + cell 47 should be tuned.