## Sheet1
Appendix A: Findings Summary
Findings/Action Items – these are items that require formal action and closure in writing for the review to be approved.
See Document SLAC-I-020-00100-001 for Design Review Requirements and Guidelines
Concerns/Recommendations – these are comments that require action by the design/engineering team, but a response
is not required to approve the review
Observations – these are general comments and require no response
Para No. |  |  | Action Item | Concern | Observn | NA | Comment
1 | a | 1 |  |  | X
|  | 2 |  |  | X
|  | 3 |  | X |  |  |  | 1. Magnetic forces and moments were scaled from the Cornell study of 2011. It should be confirmed that these forces and moments can be scaled (same size blocks, same gaps, same orientation) from the Cornell analysis and develop a specification table of maximum force and moment vs. polarity so that there is no confusion. If there have been significant block size, Br, or gap changes, the analysis or part of the analysis should be repeated or loads re-scaled.
|  | 4 |  |  | X
|  | 5 |  | X |  |  |  |  | 1. There were not any requirements listed for allowed PM block deflections in the assembled device (see magnetic requirements).
6
1 | b | 1 |  |  | X
|  | 2 |  | X | [5 empty] | 1. End design: The design suffers from phase-dependent, permeability > 1 end kicks. This effect is not obviously significant for the horizontal polarization case. Numerical simulations should be used to improve the end design (Radia or other code with u// ~ 1.07 and u┴ ~ 1.17).
|  | 3 |  | X | [6 empty] | 1. Systematic error in quadrant measurements: After CMM measurements, the phase error of a single quadrant was measured as 40°. This is a very large error for a 1 m long quadrant. A typical result for a 2 m EPU prior to tuning is less than 10°. This suggests a systematic measurement error like taper, meaning the measurement axis is tilted with respect to the quadrant axis.
|  | 4 |  |  | X
|  | 5 |  |  | X
|  | 6 |  |  | X
|  | 7 |  |  | X
|  | 8 |  |  | X
|  | 9 |  |  | X
|  | 10 |  | X | [5 empty] | 1. Needle bearings: The switch to needle bearings is a very good choice. They have high stiffness and load capacity and long lengths and can be integrated into precision machined structures and be pre-loaded. These are the bearings typically used on EPU’s between the row phases. The selected size looks to be sufficiently rigid and the small deflections from the FEA model confirm their stiffness. If needed, for envelope reasons, the next smaller size could probably be used. The bearing steel looks to be a couple of block lengths from the PM’s. A check should be that the effect on the bore field is insignificant or develop a plan to measure and tune the quadrants with the bearings in place.
|  | 11 |  |  | X
|  | 12 |  |  | X
|  | 13 |  |  | X
|  | 14 |  | X | [5 empty] | 1. Single vs. multiple carriers for each quadrant: The use of three carriers for each quadrant offers ease of handling for the installation into the strongback, but adds another source of repeatability error after the quadrants are tuned. Consider using a single carrier for each quadrant. The assembly fixturing for the carriers might be somewhat more involved but the benefit of a more repeatable assembly probably outweighs this difficulty.
|  | 15 |  | X | [6 empty] | 1. Final assembly of the quadrants and halves: The assembly procedure makes extensive use of the Leitz CMM at MMF. The plan to align and preassemble all the bearings in the strongback followed by assembly, pre-load, and CMM inspection of the carriers to allow accurate final machining of the PM mounting surfaces will maximize the repeatability of the quadrants. Care should be taken that the coordinate reference frame used for the CMM measurements matches that on the drawing for the final machining so the machinist sets up off the same datum surfaces. With this approach, it may even be possible to independently measure and tune each quadrant in its strongback half and then again as a paired quadrants in the strongback prior to final assembly. Fixturing will need to be developed for assembling the carriers and assembling the strongback halves. These fixture designs should be presented at the FDR. When designing the fixturing, keep in mind that the half strongback, C-shaped structure is not at stiff as the assembled structure and could deflect from the magnetic forces (although this deflection looks to be insignificant in X from the FEA model, Y deflection was not shown) making installation of the conical pin difficult. Fixture screws can be used to deflect the strongback back to its C shape to ensure the pin fit while fastening the two halves together. Moreover, multiple pins (not necessarily all conical, perhaps round pins match machined between the halves) can be used down the length of the device as confirmation that the strongback is in its “undeflected” shape that it had prior to magnetic loading.
|  | 16 |  | X | [6 empty] | 1. Vacuum chamber assembly: The vacuum tube will be fit down the bore of the Delta and then welded to the EVAC flange similar to what was done on LCLS-1 but it was not clear whether this will be an SST weld or an Al weld. If it is an Al weld, done with AC current, the fringe fields could cause problems. Mu metal shunts may be needed during the welding. Due to the tube sag, the chamber will contact the moving PM blocks. Care should be taken that the tube does not put excess pressure on the edge of a PM block. Making up the EVAC flange should not drive the tube harder against the PM blocks. Design issues such as tube tensioning, tube support, low friction coatings, installation fixtures, etc. should be considered and presented at the FDR.
1 | c |  |  | X |  |  | at FDR |  |  |  | Alignment tolerances and an alignment scheme for final installation Delta still need to be developed.
1 | d |  |  | X |  |  | at FDR |  |  |  | These interfaces need to be further defined: 1) attachment and alignment to the LCLS-1 girder 2) controls interface (separate review) 3) Final interface between the vacuum chamber and the undulator
1 | e |  |  |  | X |  | at FDR
2 | a |  |  |  |  | X
| b |  |  |  |  | X
| c |  |  |  |  | X
| d |  |  |  | X |  | See 1.b.12
3 | a |  |  |  | X
4 | a |  |  |  |  | X
5 | a |  |  |  |  | X
6 | a |  |  |  | X