## Sheet1
Performance Objective |  | Project Management
2.1a Construction Project Performance for Projects Greater than $250k
Project Name | TEC ($K)
Light Assembly Building Substation | 1590 |  | Cost ($K) |  |  | Completion Schedule
|  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2004-01-01 | 2004-01-01
ED&I/Project Management |  |  | 127 | 140.4 |  | 2005-09-01 | 2005-09-01
Procurement/Construction |  |  | 1345 | 1266.6 |  | 2005-09-01 | 2005-09-01
Indirect |  |  | 118 | 127.6
Beneficial Use | [5 empty] | 2005-09-01 | 2005-09-01
Project Completion | [5 empty] | 2005-10-01
Replace LINAC VVS | 561 |  | Cost ($K) |  |  | Completion Schedule
(16 total @ $561K/ea) |  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2004-05-01 | 2004-07-01
ED&I/Project Management |  |  | 52 | 0.8 |  | 2005-12-01
Procurement/Construction |  |  | 429 | 31.9
Indirect |  |  | 80 | 2.5 |  | 2005-09-01
2005-10-01
Beneficial Use | [5 empty] | 2005-10-01
Project Completion | [5 empty] | 2005-12-01
Building 751 Remodel (CEH) | 293 | 293 | Cost ($K) |  |  | Completion Schedule
|  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval
ED&I/Project Management |  |  | N/A | N/A |  | 2005-06-01 | 2005-06-01
Procurement/Construction |  |  | 293 | 167.3 |  | 2005-06-01 | 2005-06-01
Indirect |  |  |  | 8
Beneficial Use | [5 empty] | 2005-09-01 | 2005-09-01
Project Completion | [5 empty] | 2005-10-01
HVAC Upgrade SCS 1st and 2nd Floor | 478 |  | Cost ($K) |  |  | Completion Schedule
|  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2002-09-01 | 2002-09-01
ED&I/Project Management |  |  | 36 | 19 |  | 2005-10-01
Procurement/Construction |  |  | 402 | 374.5 |  | 2005-10-01
Indirect |  |  | 40 | 36.9
Beneficial Use | [5 empty] | 2005-10-01
Project Completion | [5 empty] | 2005-10-01
SLAC 10gb Network Upgrade | 823 | 400 | Cost ($K) |  |  | Completion Schedule
|  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 1998-01-13 | 1998-01-13
ED&I/Project Management |  | ED&I |  |  |  | 2006-09-01
Procurement/Construction |  | Const | 777 | 788.7
Indirect |  | Indirect | 46 | 34 |  | 2006-09-01
Beneficial Use | [5 empty] | 2006-09-01
Project Completion | [5 empty] | 2006-09-01
Upgrade Substation 7 | 1103 |  | Cost ($K) |  |  | Completion Schedule
|  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2002-09-01 | 2002-09-01
ED&I/Project Management |  | ED&I | 125 | 118.2 |  | 2005-10-01
Procurement/Construction |  | Const | 822 | 697.3 |  | 2005-10-01
Indirect |  | Indirect | 156 | 148.3
Beneficial Use | [5 empty] | 2005-10-01
Project Completion | [5 empty] | 2005-10-01
Secondary Containment Upgrade | 270 |  | Cost ($K) |  |  | Completion Schedule
for PEP II |  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2003-03-01 | 2003-03-01
ED&I/Project Management |  | ED&I | 25 |  |  | 2006-11-01
Procurement/Construction |  | Const | 211 | 28.4 |  | 2006-11-01
Indirect |  | Indirect | 34 | 6
Beneficial Use | [5 empty] | 2006-11-01
Project Completion | [5 empty] | 2006-11-01
Seismic upgrade for | 436 |  | Cost ($K) |  |  | Completion Schedule
ESB/Shield Upgrade |  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2002-11-01 | 2002-11-01
ED&I/Project Management |  | ED&I | 64 | 84.8 |  | 2006-11-01
Procurement/Construction |  | Const | 331 | 79.3 |  | 2006-11-01
Indirect |  | Indirect | 41 | 30.8
Beneficial Use | [5 empty] | 2006-11-01
Project Completion | [5 empty] | 2006-11-01
Klystron Gallery Equip Grounding | 400 |  | Cost ($K) |  |  | Completion Schedule
|  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2002-09-01 | 2002-09-01
ED&I/Project Management |  | ED&I | 18 | 1.1 |  | 2005-10-01
Procurement/Construction |  | Const | 304 | 310.3 |  | 2005-10-01
Indirect |  | Indirect | 78 | 85.5
Beneficial Use | [5 empty] | 2005-10-01
Project Completion | [5 empty] | 2005-10-01
SCS Cooling-Replace Fan | 335 |  | Cost ($K) |  |  | Completion Schedule
and Cooling Coil |  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2005-03-01 | 2005-03-01
ED&I/Project Management |  | ED&I | 51 | 9.9 |  | 2006-01-01
Procurement/Construction |  | Const | 284 | 7.5 |  | 2006-01-01
Indirect |  | Indirect |  | 0.4 |  | 2006-01-01
Beneficial Use | [5 empty] | 2006-01-01
Project Completion | [5 empty] | 2006-01-01
Alpine Gate Road and Drainage | 512 |  | Cost ($K) |  |  | Completion Schedule
|  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2006-07-01 | 2006-07-01
ED&I/Project Management |  | ED&I | 44 | 9 |  | 2005-11-01
Procurement/Construction |  | Const | 468 |  |  | 2005-06-01
Indirect |  | Indirect |  |  |  | 2005-11-01
Beneficial Use | [5 empty] | 2005-11-01
Project Completion | [5 empty] | 2005-11-01
Replace LINAC K1A and K1B | 426 |  | Cost ($K) |  |  | Completion Schedule
|  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2005-03-01 | 2005-03-01
ED&I/Project Management |  | ED&I | 17 | 19.2 |  | 2005-11-01
Procurement/Construction |  | Const | 381 | 156.8
Indirect |  | Indirect | 28 | 17.6 |  | 2005-11-01
Beneficial Use | [5 empty] | 2005-11-01
Project Completion | [5 empty] | 2005-11-01
Re Roof Cryo BLDG 006 Low Bay | 466 |  | Cost ($K) |  |  | Completion Schedule
|  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 2005-04-01 | 2005-04-01
ED&I/Project Management |  | ED&I | 31 | 33.5 |  | 2005-11-01
Procurement/Construction |  | Const | 400 | 128.3
Indirect |  | Indirect | 35 | 20.8 |  | 2005-11-01
Beneficial Use | [5 empty] | 2005-11-01
Project Completion | [5 empty] | 2005-11-01
X-ray Laboratory for Advanced Material | 1400 |  | Cost ($K) |  |  | Completion Schedule
|  |  | Plan | Actual | actual/plan | Plan | Actual | actual/plan
NEPA Approval | [5 empty] | 1996-08-01 | 1996-08-01
ED&I/Project Management |  | ED&I | 100 | 122 |  | 2004-12-01
Procurement/Construction |  | Const | 1171 | 643 |  | 2005-08-01
Indirect |  | Indirect | 129 | 55 |  | 2005-08-01
Beneficial Use | [5 empty] | 2006-01-01
Project Completion | [5 empty] | 2006-06-01